## Scope of work
Administrator
Task | Subtask | Details | No. months under contract (2.5 years)* | Hours/ month | Total hours
Administration | Strategy Planning Discussion with Administrator, and any key ACCG members, as appropriate | Review upcoming Admin WG, general, and Planning WG meeting agendas; strategize on topics and next steps. | 15 | 2 | 30
Administration | General meeting and Admin Work Group meeting preparation | Agenda and meeting material development, coordinate with guest speakers, press releases, and meeting material email distribution. | 28 | 2 | 56
Facilitation | Facilitate Admin WG meetings | Admin WG host and facilitatator of meetings. | 28 | 2 | 56
Administration | Host and attend general meetings | Host/attend general meetings and assist volunteer Facilitator (in-person meeting travel time included - assuming 2.5 hour meetings, 45 min of meeting room set up and take down, and 2 hour, or less, roundtrip travel time). Note: If meetings are held virutally only, travel time and meeting room set-up/take-down time do not apply. | 28 | 5.25 | 147
Administration | General meeting summary | Draft general meeting summaries. | 28 | 2 | 56
Administration | Admin WG meeting action items | Draft and distribute Admin WG meeting action items. | 28 | 1 | 28
Administration | Planning WG meeting preparation | Agenda and meeting material development and distribution. | 26 | 1 | 26
Facilitation | Facilitate Planning WG meetings | Faciliate and host/attend meetings (in-person meeting travel time included - assuming 3 hour meetings, 45 min for meeting room set up and take down, and 2 hour, or less, roundtrip travel time). Note: If meetings are held virutally only, travel time and meeting room set-up/take-down time do not apply. | 26 | 5.75 | 149.5
Administration | Planning WG meeting summary | Draft and distribute Planning WG meeting summaries. | 26 | 2 | 52
Administration | ACCG outreach/website | Post meeting materials to website; share articles with ACCG listserv and post to website; share member news with ACCG listserv and post to website; website maintenance. | 30 | 4.5 | 135
|  | Total hours for contract (*2.5 years equates to 28 general meetings (no Dec. meetings), 28 Admin WG meetings (no Dec. meetings), and 26 Planning WG meetings (usually no Nov. or Dec. meetings, may vary) |  |  | 735.5
Professional Facilitation Support Contractor(s)
Task | Subtask | Details | Total hours budgeted for grant
Administration | Strategy Planning Discussion with Administrator, and any key ACCG members, as appropriate | Review upcoming Admin WG, general, and Planning WG meeting agendas; strategize on topics and next steps | 30 (2 hrs/month for first 15 months)
Facilitation | Meeting Facilitation and Conflict Resolution (additional cost for travel time) | Provide mediation services for conflict resolution support (including planning, shuttle diplomacy, facilitation, and follow up activities) on an as needed basis. | 30 (as needed)
Administration | Foundational Document Preparation by Lead Facilitation Contractor | Provide support to ACCG Administrator to update foundational documents and prepare other materials to support the ACCG's collaboration (e.g., strategic plan update, communications and engagement plan update, collaboration strategy updates, etc. | 20
Administration | Foundational Document Preparation by Associate Facilitation Contractor |  | 10
Administration | Foundational Document Preparation by Support Facilitation Contractor |  | 10
|  | Total hours for contract | 100