ACCG December Monitoring Meeting

Wednesday, December 10, 2025

Next Meeting:

January 14 2026 – virtual meeting

Updates from November meeting

- Review task list from our November meeting

- Make sure to participate on Special Sessions

MAC Planning Updates

MAC Planning Team is hard at work wrapping things up

Modelling team effort is still ongoing and we will continue to weave metrics into modelling

  - This is important for our group to have metrics for monitoring

End of January/February public comment period will be open

- Response to Comments - came to planning workgroup - Forest Service

- Wil be included in package for the Part 2 public comment period so record of response will happen

- UMWRA will be stepping back from the process mid to late January

MAC Monitoring Strategy Updates – Special Sessions

- We have had 2 Special Session Meetings

- Native American Tribal Questions related to TEK

  - Tribal implementation and resource protection monitoring questions

  - Two implementation questions that we refined in the special session

  - Discussion of effectiveness question - design a new one or have a focus on TEK in existing relevant questions

- Overstory and Habitat Questions

  - We discussed the indicators and made some progress on developing the expanded table

- Next meetings:

  - December 11 0900-1000 – Fire Special Session

  - December 111000-1100 - Implementation Special Session

  - December 12 0900-1100 - Wildlife Special Session

  - Understory/Species of Concern – will reschedule this meeting

  - Overstory Special Session #2 – will schedule second meeting

- Box Folder for materials - https://usfs.box.com/s/b7o46736d0lrb6ggahwqwfwphpbb0sqw

Monitoring Meeting

- Presentation of draft questions at January full ACCG meeting – January 21

- 30/45 minutes presentation with questions

- Background, Questions with Example of who we are applying each broad question - how can we flesh this out so that folks can understand, Next Steps for Strategy Documents/Timeline/next steps, Integration with FEIS and ACCG Monitoring Strategy

- Clean up questions for the full ACCG monitoring meeting in January

- January monitoring meeting agenda - review the draft questions

Mastication/Fuelbreaks Discussion (Helen)

- Monitoring related to fuels reduction/mastication

- Mulched mastication v. Regular mastication and impacts on shrubs and native species

- Interest from the BIG group on the Basin and CDFW - game biologist tracking mule deer along the Hwy 88 corridors

- Management of wildlife corridors - CDFW moving forward with game cameras and ARUs

- Deployment within the MAC project

- Task Follow up: Reach out to Forest Service and UMWRA to deploy in the MAC project

- WCB - vegetation monitoring/understory and longevity of treatment and Implementation - meeting criteria for fuels reductions

- WCB can apply at any time - not accepting applications since Prop 4 funding

- Might not be until May for letters of interest

- Any other monitoring sources or funding that might be related to this

- Mechanical mastication and prescribed burning reduce forest fuels and alter stand structure in dry coniferous forests - reference

Task List:

- Need to schedule another Overstory meeting with the special session group

- Email to everyone to reschedule the understory veg/overstory veg for good dates and times

- Review the other reports for additional metrics from MAC Planning

- Make sure others have invitations to special session meetings - understory veg and wildlife and put up schedule for the working group meetings

- Develop new working timeline for monitoring strategy and next steps to incorporate FEIS after finalization

- Do we need to develop a question related to mastication/fuel breaks for understory vegetation? Scale of operation.

- Reach out to Forest Service and UMWRA to deploy in the MAC project